## Tabelle1
[11 empty] | ID | WP | Name | Expected Publication Date
D2.1 | Branding Strategy | 1-IRT | WP2 | M2 | 2 | 1 | 2 | 2015 | 2015-02-01 | 2015-02-28 | D2.1 | WP2 | Branding Strategy | 2015-02-27
D2.2 | Dissemination and Communication Plan | 6-UvA | WP2 | M3 | 3 | 1 | 3 | 2015 | 2015-03-01 | 2015-03-31 | D2.2 | WP2 | Dissemination and Communication Plan | 2015-03-31
D2.3 | Updated Dissemination and Communication Plan | 6-UvA | WP2 | M11 | 11 | 1 | 11 | 2015 | 2015-11-01 | 2015-11-30 | D2.3 | WP2 | Updated Dissemination and Communication Plan | 2015-11-30
D2.4 | Final Dissemination and Communication Plan | 6-UvA | WP2 | M23 | 23 | 1 | 11 | 2016 | 2016-11-01 | 2016-11-30 | D2.4 | WP2 | Final Dissemination and Communication Plan | 2016-11-30
D2.5 | Annual report on dissemination activities and public participation and awareness - Year 1 | 6-UvA | WP2 | M12 | 12 | 1 | 12 | 2015 | 2015-12-01 | 2015-12-31 | D2.5 | WP2 | Dissemination Report - Year 1 | 2015-12-31
D2.6 | Annual report on dissemination activities and public participation and awareness - Year 2 | 6-UvA | WP2 | M24 | 24 | 1 | 12 | 2016 | 2016-12-01 | 2016-12-31 | D2.6 | WP2 | Dissemination Report - Year 2 | 2016-12-30
D2.7 | Annual report on dissemination activities and public participation and awareness - Final | 6-UvA | WP2 | M35 | 35 | 1 | 11 | 2017 | 2017-11-01 | 2017-11-30 | D2.7 | WP2 | Dissemination Report - Final | 2017-11-30
D3.1 | Evaluation of Use Cases | 7-CNRS | WP3 | M10 | 10 | 1 | 10 | 2015 | 2015-10-01 | 2015-10-31 | D3.1 | WP3 | Evaluation of Use Cases | 2015-10-30
D3.2 | Consolidated Evaluation of Use Cases | 7-CNRS | WP3 | M22 | 22 | 1 | 10 | 2016 | 2016-10-01 | 2016-10-31 | D3.2 | WP3 | Consolidated Evaluation of Use Cases | 2016-10-31
D3.3 | Final Evaluation of Use Cases | 7-CNRS | WP3 | M34 | 34 | 1 | 10 | 2017 | 2017-10-01 | 2017-10-31 | D3.3 | WP3 | Final Evaluation of Use Cases | 2017-10-31
D3.4 | Business Plans and Potential Market | 1-IRT | WP3 | M35 | 35 | 1 | 11 | 2017 | 2017-11-01 | 2017-11-30 | D3.4 | WP3 | Business Plans and Potential Market | 2017-11-30
D3.5 | Overview of Implemented Use Cases | 7-CNRS | WP3 | M36 | 36 | 1 | 12 | 2017 | 2017-12-01 | 2017-12-31 | D3.5 | WP3 | Overview of Implemented Use Cases | 2017-12-29
D4.1 | Security infrastructure specification and initial implementation | 4-TUB | WP4 | M12 | 12 | 1 | 12 | 2015 | 2015-12-01 | 2015-12-31 | D4.1 | WP4 | Security infrastructure specification and initial implementation | 2015-12-31
D4.2 | Multi-cloud security | 4-TUB | WP4 | M24 | 24 | 1 | 12 | 2016 | 2016-12-01 | 2016-12-31 | D4.2 | WP4 | Multi-cloud security | 2016-12-30
D4.3 | CYCLONE secure action and resource models | 4-TUB | WP4 | M12 | 12 | 1 | 12 | 2015 | 2015-12-01 | 2015-12-31 | D4.3 | WP4 | CYCLONE secure action and resource models | 2015-12-31
D4.4 | Consolidated CYCLONE secure action and resource models | 4-TUB | WP4 | M24 | 24 | 1 | 12 | 2016 | 2016-12-01 | 2016-12-31 | D4.4 | WP4 | Consolidated CYCLONE secure action and resource models | 2016-12-30
D4.5 | Final CYCLONE secure action and resource models | 4-TUB | WP4 | M36 | 36 | 1 | 12 | 2017 | 2017-12-01 | 2017-12-31 | D4.5 | WP4 | Final CYCLONE secure action and resource models | 2017-12-29
D5.1 | Functional specification of the E2E Network service model | 5-I2CAT | WP5 | M7 | 7 | 1 | 7 | 2015 | 2015-07-01 | 2015-07-31 | D5.1 | WP5 | Functional specification of the E2E Network service model | 2015-07-31
D5.2 | Specification of network management and service abstraction | 5-I2CAT | WP5 | M15 | 15 | 1 | 3 | 2016 | 2016-03-01 | 2016-03-31 | D5.2 | WP5 | Specification of network management and service abstraction | 2016-03-31
D5.3 | Cloud federation Network Service delivery and integration | 5-I2CAT | WP5 | M36 | 36 | 1 | 12 | 2017 | 2017-12-01 | 2017-12-31 | D5.3 | WP5 | Cloud federation Network Service delivery and integration | 2017-12-29
D6.1 | Complex Application Description Specification | 2-SIXSQ | WP6 | M6 | 6 | 1 | 6 | 2015 | 2015-06-01 | 2015-06-30 | D6.1 | WP6 | Complex Application Description Specification | 2015-06-30
D6.2 | Specification of Interfaces for Brokering, Deployment, and Management | 2-SIXSQ | WP6 | M8 | 8 | 1 | 8 | 2015 | 2015-08-01 | 2015-08-31 | D6.2 | WP6 | Specification of Interfaces for Brokering, Deployment, and Management | 2015-08-31
D6.3 | Solutions for Non-functional Aspects of Cloud Applications | 6-UvA | WP6 | M21 | 21 | 1 | 9 | 2016 | 2016-09-01 | 2016-09-30 | D6.3 | WP6 | Solutions for Non-functional Aspects of Cloud Applications | 2016-09-30
D6.4 | Summary of Provided Brokering, Deployment, and Management Features | 4-TUB | WP6 | M33 | 33 | 1 | 9 | 2017 | 2017-09-01 | 2017-09-30 | D6.4 | WP6 | Summary of Provided Brokering, Deployment, and Management Features | 2017-09-29
D7.1 | Description of testbed | 3-QSC | WP7 | M7 | 7 | 1 | 7 | 2015 | 2015-07-01 | 2015-07-31 | D7.1 | WP7 | Description of testbed | 2015-07-31
D7.2 | Overlay with focus on component manager | 3-QSC | WP7 | M10 | 10 | 1 | 10 | 2015 | 2015-10-01 | 2015-10-31 | D7.2 | WP7 | Overlay with focus on component manager | 2015-10-30
D7.3 | Overlay with focus on resource manager and SDN | 3-QSC | WP7 | M16 | 16 | 1 | 4 | 2016 | 2016-04-01 | 2016-04-30 | D7.3 | WP7 | Overlay with focus on resource manager and SDN | 2016-04-29
D7.4 | Inclusion of features asked by developers | 3-QSC | WP7 | M30 | 30 | 1 | 6 | 2017 | 2017-06-01 | 2017-06-30 | D7.4 | WP7 | Inclusion of features asked by developers | 2017-06-30

## deliverables
ID | WP | Name | Expected Publication Date
D2.1 | WP2 | Branding Strategy | 2015-02-27
D2.2 | WP2 | Dissemination and Communication Plan | 2015-03-31
D2.3 | WP2 | Updated Dissemination and Communication Plan | 2015-11-30
D2.4 | WP2 | Final Dissemination and Communication Plan | 2016-11-30
D2.5 | WP2 | Dissemination Report - Year 1 | 2015-12-31
D2.6 | WP2 | Dissemination Report - Year 2 | 2016-12-30
D2.7 | WP2 | Dissemination Report - Final | 2017-11-30
D3.1 | WP3 | Evaluation of Use Cases | 2015-10-30
D3.2 | WP3 | Consolidated Evaluation of Use Cases | 2016-10-31
D3.3 | WP3 | Final Evaluation of Use Cases | 2017-10-31
D3.4 | WP3 | Business Plans and Potential Market | 2017-11-30
D3.5 | WP3 | Overview of Implemented Use Cases | 2017-12-29
D4.1 | WP4 | Security infrastructure specification and initial implementation | 2015-12-31
D4.2 | WP4 | Multi-cloud security | 2016-12-30
D4.3 | WP4 | CYCLONE secure action and resource models | 2015-12-31
D4.4 | WP4 | Consolidated CYCLONE secure action and resource models | 2016-12-30
D4.5 | WP4 | Final CYCLONE secure action and resource models | 2017-12-29
D5.1 | WP5 | Functional specification of the E2E Network service model | 2015-07-31
D5.2 | WP5 | Specification of network management and service abstraction | 2016-03-31
D5.3 | WP5 | Cloud federation Network Service delivery and integration | 2017-12-29
D6.1 | WP6 | Complex Application Description Specification | 2015-06-30
D6.2 | WP6 | Specification of Interfaces for Brokering, Deployment, and Management | 2015-08-31
D6.3 | WP6 | Solutions for Non-functional Aspects of Cloud Applications | 2016-09-30
D6.4 | WP6 | Summary of Provided Brokering, Deployment, and Management Features | 2017-09-29
D7.1 | WP7 | Description of testbed | 2015-07-31
D7.2 | WP7 | Overlay with focus on component manager | 2015-10-30
D7.3 | WP7 | Overlay with focus on resource manager and SDN | 2016-04-29
D7.4 | WP7 | Inclusion of features asked by developers | 2017-06-30